## Risk
Potential Risks | Risk Mitigation Measures | Justification
Security Attacks | Review current security protocols and procedures to ensure that the cuurent requirements to this project are acceptable | Sofware reuse or extending the deadline will allow for current personnel. Adding additional team members will also mitigate this risk without deadline extension
Unrealistic Schedule | Extend deadlines; review current use cases and remove any unecessary tasks; add team members | Adding a 4th iteration would helpful. Especially due to the complexity and priority of UC09
Shortage of Resources | Add additional resources; look into more efficient methods using allocating current resources; primary area of concern is iteration 2 with regards to UC9 | The is imperative to the success of the project. UC9 comprises over 1/3 of the entire timeline and any necessary measures need to implented to ensure the projects success.
Communication Challenges | Due to the need for online collaboration with this project and the assumption of additonal parties from other countries caution must be excercised to ensure that all parties understand their responsibilities and other parties have conveyed their expecatations or the project team members hace concluded and agrred that the timelines and expectations are reasonable | This one critcal risk mitigation factor is essential to the overall success of the project. The current timeline is stringent and we cannot afford the luxury of additional time to accommodate for this issue.
Personnel Shortfall | Addition of a Database team member | The complexities associated with the security of information merit expertise in this area.